MICHIGAN

DEPARTMENT OF TRANSPORTATION

SPECIAL PROVISION

FOR

ELECTRICAL SERVICE WORK FOR JOB NUMBER 204305

OAK:KHC	1 of 2	APPR:BMB:NJM:07-03-24

a.	Description.  This work consists of de-energizing the two existing electrical services for the I-696 structure Z03 of 63102 under bridge lighting, relocating utility service feeds and existing service equipment, and reconnection of the electrical services.  This includes steel support rack, meter enclosure, control transformer (CT) cabinet, utility pad-mount transformers, transformer pads, mounting brackets, hardware, fittings, cables, connectors, grounding, and other materials required to complete the electrical work as shown on the plans or as directed by the Engineer.  Storage and disposal of material is also included in the item and will not be paid for separately.

Coordinate all electrical service requirements with:

DTE Energy

Redford, MI 48239

Tyler Kreft

Phone:  313-235-9578

Email:  tyler.kreft@dteenergy.com

Work Order Numbers:  72998183 and 72998343

b.	Materials.  Furnish materials in accordance with section 918 of the Standard Specifications for Construction, local codes, and the requirements of this special provision.  Furnish all hardware and miscellaneous items required to relocate existing electrical service equipment.  Furnish all new materials free from damage.

c.	Construction.  As soon as the contract is awarded, contact the utility company to have all utility services operational within the established time frame.  No additional payment, due to any delay caused by the utility feed(s) and removals not being completed will be made.

1.	DTE work order 72998343 (Southwest Church Street).  Work consists of disconnecting the existing electrical service, removing the primary feed at the existing pad-mount transformers back to the utility pole, installing new raceway from utility pole to existing pad-mount transformers to avoid excavation work for the existing Z03 structure reconstruction, and reconnecting the electrical service.  Existing transformers, meter, CT cabinet, and MDOT electrical distribution panels to remain.

Power to the existing freeway lighting electrical distribution system served by this electrical service is required to be maintained during Z03 construction work for operation of temporary under bridge lighting.  Coordinate relocation of the electrical service primary feed with utility to accommodate the lighting construction requirement, or arrange with utility company for temporary electric service, including payment of utility company charges for service.

2.	DTE work order 72998183 (Southeast Church Street).  Work consists of disconnecting the existing electrical service, removing the primary feed at the existing pad-mount transformers back to the utility pole, salvaging and relocating the existing pad-mount transformers, steel support rack, CT cabinet, and metering enclosure to avoid excavation work for the existing Z03 structure reconstruction, furnishing concrete transformer pads, installing new raceway from utility pole to pad-mount transformers, and reconnecting the electrical service.  Existing MDOT electrical distribution panels to remain.

Power to the existing freeway lighting electrical distribution system served by this electrical service is not required to be maintained during Z03 construction work.  Reconnection of the electrical service to be finished upon completion of Z03 excavation work.

Coordinate utility service outages and exact requirements with utility company.  Ensure equipment is bonded as required by the NEC, the Utility, and the MDOT standards.  Ensure all work conforms to sections 818 and 819 of the Standard Specifications for Construction, the applicable details, and local codes.

d.	Measurement and Payment.  The completed work, as described, will be measured and paid for at the contract unit price using the following pay items:

Pay Item	Pay Unit

Elec Serv, Southwest Church Street	Each

Elec Serv, Southeast Church Street	Each

1.	Elec Serv, Southwest Church Street includes all work and incidental items required for disconnecting the existing electrical service, relocating the utility primary feed, and reconnection of the electrical service for a complete and operating system.

2.	Elec Serv, Southeast Church Street includes all work and incidental items required for disconnecting the existing electrical service, salvaging and relocating the existing service equipment, new transformer pads, relocating the utility primary feed, and reconnection of the electrical service for a complete and operating system.  Secondary cables and conduits from DTE service point to MDOT distribution equipment will be paid for separately.