## Comment Log
Project Name: | I-94/US-131 System Interchange Analysis
Project Number: | 194403A
Project Manager: | Lauren Warren
Initials: | MJH = Matthew John Hill, PE, PTOE / TJK = Trevor J Kirsch, MS, EIT
Comment # | Document Name | Stage | Page/Section/File Name | Comment | Comment By | Date of Comment | Action Taken/Response | Response By | Date of Response | Final Status | Approved By | Date Approved
1 |  |  | Existing VISSIM Model | Modeling limits need to be extended to the west to include the WB I-94 exit and entrance ramps to/from 9th Street. | MJH | 2019-10-03 | Model limits extended to include 9th St on and of ramps | TJK | 2019-10-04 | Complete | MJH | 2019-10-08
2 |  |  | Existing VISSIM Model | Extend WB 94 entry link further to the east (east of Portage Road interchange) to allow for entering traffic to position adequately for exiting at Westnedge without artificially creating congestion from last second lane changes. | MJH | 2019-10-03 | Extended I-94 WB entry link | TJK | 2019-10-04 | Complete | MJH | 2019-10-08
3 |  |  | Existing VISSIM Model | Behavior type for freeway links should be set to a freeway free lane selection behavior type. | MJH | 2019-10-03 | Behavior type adjusted for all freeway links | JMP | 2019-10-04 | Complete | MJH | 2019-10-08
4 |  |  | Existing VISSIM Model | Extend link 2 all the way back to where the decel lane taper begins per modeling best practices and adjust connector accordingly (seek to keep connectors as short as possible in general but still visible for reviewing/adjusting). | MJH | 2019-10-03 | Extended Link 2 to the decel lane taper and adjusted the connector | TJK | 2019-10-04 | Complete | MJH | 2019-10-08
5 |  |  | Existing VISSIM Model | Extend link 2 all the way to the gore where the striping splits (it's close, but lets capture every inch of allowable lane changing space for general modeling practice). Connectors should be adjusted so that they start right at the end of Link 2 and do not overlap link 2 much. Keep short. | MJH | 2019-10-03 | Extended Link 2 to the striping split and adjusted the connectors | TJK | 2019-10-04 | Complete | MJH | 2019-10-08

## Drop Down Menus
Type of Documents | Stage
Clearance Interval Spreadsheet | Preliminary
CORSIM model | OEC | PM can add additional options for drop down
Cost Estimate | Draft
Counts | Final
Crash Analysis
HCS
Highway Safety Manual
Intersection Photos
Inventory Forms
Microsimulation Spreadsheet
MOT
Report
SAPW
Signal Design
Sim Traffic
Synchro Models
Timing Permits
TOD/FS
Travel Demand Forecasting
Trip Generation/Distribution
Existing VISSIM model
Preliminary Design Report
Electrical Calculations
Communication Drawings
Link Budgets
Construction Drawings
Cost Estimate
Specifications
Details
Structures/Geotechnical
Environmental